## Table of Contents
Links
Recovery 25-26 BOM
STAR Bill of Materials 2025
Excalibur
1) Parachute Sizing
2) 2 Parachute Shockloading
2) 3 Parachute Shockloading
3) Component Selection
4) Ejection Charges & Shear Pins
5) Vent Hole Sizing
6) Power Budget
7) Thread Strength
8) Annulus Design
9) Flight CONOPS Specs
Shockcord Testing Results Fa24
Recovery Flight Log

## Tasks
f | CATEGORY | Column 3 | DESCRIPTION | PARAMETERS | ACTION ITEMS | START DATE | END DATE | RESPONSIBLE ENGINEER | DONE | WORKING LINK/ UPDATES/SOPs | REQUIRED HARDWARE/FACILITIES/APPROVALS
Crimp Quality | Vehicle | 1. High | Training and quality of homemade crimps |  |  | 2025-11-03 | 2025-11-13 | Daniel Wiley Richards | TRUE
Radial Bulkhead Testing | Testing | 1. High | Design a testing article for testing a subscale radial bulkhead |  | 3in - Calculations for #radial screws (fiberglass tearout) - Placement of scale U-bolts - Pocketing if needed - Overall thickness - Instron bulkhead retention plate - Instron compression platen spacer 6in: | 2025-11-03 | 2025-11-06 | Angelo Alexander Andal | FALSE
Blue Raven Testing | Testing | 1. High | Figure out what the hell went wrong with the Blue Ravens |  |  | 2025-10-23 | 2025-11-06 |  | TRUE
Line Cutter Test | Testing | 1. High | Devise a realistic test for line cutters | - Must ensure reliability of line cutters - Must ensure line cutters don't yank wires out of av bay/GX12s for LE3 - Must ensure retention of line cutters | - similar confidence test, calculations, etc as pyrobolts | 2025-10-20 | 2025-10-30 | Rebekah Elizabeth Clark Jocelyn Janet Jimenez | FALSE
AV Bay CAD | Vehicle | 1. High | Make complete CAD (with mass!) for Solid Demo/LE3 | Make it strong, no structural 3d prints | Make it | 2025-10-23 | 2025-10-30 | Anton Vladimir Bogak | FALSE
GPS and Blue Raven Testing | Testing | 1. High | Confirm all Blue Ravens ____??? and Featherweight GPS and Fluctus can establish lock over similar conditions to flight profile | Epoxy down the electronics that are attached at weak joints |  | 2025-09-15 | 2025-11-03 | Anton Vladimir Bogak | FALSE
Parachute Bag | Vehicle | 1. High | Sew new parachute bag for LE3 main parachute |  | Find nomex and non-flammable elastic (ideally sponsored/free) Create pattern from existing homemade parachute bag design Scale for larger parachute (once acquired) Sew and test | 2025-09-04 | 2025-11-13 | Laura Jane Wong | FALSE
Finger Trap Shock Cord Testing | Shockloading | 1. High | Determine if "finger trapping", or splicing, kevlar shock cord is stronger/higher rated than bowline knots |  | Read this forum post Figure out how to splice 1/2" shock cord Make testing plan/SOPs | 2025-09-11 | 2025-10-30 | Elise Jiaxin Fan Laura Jane Wong | FALSE | Fall25 Shock Cord Loop Strength Testing Procedures | Instron
Test U-Bolts and Eyebolts | Testing | 1. High | Run load tests on U bolts and Eye bolts, compare loads and force distribution |  | - Waterjet U-bolt/eyebolt test plate and spacers - Get large bolts from RFS - Fit check at Hesse - Book and conduct testing | 2025-09-12 | 2025-11-06 | Elise Jiaxin Fan | FALSE | Fall25 U-Bolt Testing Procedures
Validate BLE Switch during Ground Test | Testing | 1. High | Check whether or not BLE switch works via a ground test |  |  | 2025-09-15 | 2025-10-15 |  | FALSE
Recovery Wiring Diagram | Vehicle | 1. High | Determine which electronics are flying, draw a wiring diagram |  |  | 2025-10-23 | 2025-10-27 | Daniel Wiley Richards Anton Vladimir Bogak | TRUE
Soft Link Testing | Testing | 1. High | Test 4 wraps of a soft link until full failure | Have failure rating of soft link | Schedule Hesse, go test | 2025-09-01 | 11/6//25 | Elise Jiaxin Fan | FALSE | Fall25 Soft Link and Quick Link Testing Procedures | https://www.apogeerockets.com/Building-Supplies/Recovery-Equipment/Quick-Links/Large-Soft-Link
N-body dynamics of multi-parachute systems | R&D | 1. High | Write an accurate simulator for how N parachutes affect rocket shock load and inertial load | Kush approves Agrees with numbers from Glennis | Inertial Loading | 2025-09-01 | 2025-11-06 | Manank Hemalkumar Doshi | FALSE
High Temp Wire Testing | Testing | 2. Mid | Figure out if resistance changes with temp, or if ematch will melt with charge | [5 empty] | FALSE
Flight Sim | Vehicle | 2. Mid | Write a program to show pitch, roll, and yaw of the rocket | Successfully decodes quaternions into understandable pitch, roll, yaw |  | 2025-10-20 | 2025-11-03 | Elise Jiaxin Fan | FALSE
Parachute Reefing | R&D | 2. Mid | Reef a parachute successfully |  | - Calculate effective area of reefed parachute and expected shock load/drag/descent velocity - Modify a 58" flat - If no reflight, devise a test to test it effectively (drop? skydive?) | 2025-10-20 | 2025-11-06 | Laura Jane Wong Chloe Plum Stevens | FALSE
Redesign AV Bay Removable Bulkhead | Vehicle | 2. Mid | Redesign AV Bay removable bulkhead with required hardware for drogue harness, potentially redesign with better bolt distribution |  | Determine drogue shockloading Find rated U-Bolts Determine mounting for possible HABP charge wells Redesign bulkhead for charge wells, U-Bolts, anything else Prove it can withstand drogue shockloading by FEA | 2025-08-03 | 2025-10-30 |  | FALSE
Update CONOPs | Vehicle | 2. Mid | [5 empty] | Elise Jiaxin Fan | FALSE
Quicklink Failure Test | Testing | 3. Low | Determine FOS quicklinks |  |  |  |  | Elise Jiaxin Fan | FALSE | Fall25 Soft Link and Quick Link Testing Procedures
Shockcord Bundling | Shockloading | 3. Low | Determine how to test the effect of bundling shockcord on shockloading (Instron? drop test?) |  | Make a testing plan to discuss Write SOPs Make a BOM | 2025-10-01 | 2025-10-21 | Manank Hemalkumar Doshi | FALSE | Fall25 Shockcord Bundling Testing Procedures | Instron
Parachute Inflation TIme | Shockloading | 3. Low | Devise a test to determine the inflation time of our parachutes |  | -Go to RFS | 2025-09-06 | 2025-09-06 |  | FALSE
Altimeter Testing | Testing | 3. Low | Confirm 3 altimeters missing data from test launch boot into flight mode and data collection |  |  | 2025-09-15 | 2025-10-01 |  | FALSE
Vibe Testing | Testing | 3. Low | Run RF sims on full avionics bay Conduct vibrational testing for worst-case scenario to validate and determine factor of safety for components, wiring connectors, etc. |  | Prepare a full copy of the avionics bay - bulkheads, sled, drilled holes, etc. Design a secure mount for the tube to the SSL vibration table | 2026-01-01 | 2026-02-01 | Anton Vladimir Bogak | FALSE |  | SSL vibe testing facilities (contact long in advance)
HABP | Vehicle | 3. Low | Research HABP charges (charge wells? gas? vinyl tubing?) See what Jim Jarvis, other 30k IREC/liquids teams, etc have done Determine best method and how it would be implemented on Solid Demo/LE3 | Full combustion of black powder in a charge in a vacuum | Make a testing plan to discuss Reach out to sponsors/labs for access to vacuum chamber Write SOPs Make a BOM | 2026-01-01 | 2026-05-01 |  | FALSE |  | Explosives testing approval from CoE (or armored car lot if not)
Shockcord Strength | Shockloading | 3. Low | Determine pure cord strength of 1/2" kevlar shockcord |  | Design an Instron-friendly mount that puts the cord in pure tension via pulleys and can withstand 55+ kN |  | \ | Manank Hemalkumar Doshi | FALSE |  | Instron
Y-Harness Failure Testing | Testing | 3. Low | [6 empty] | FALSE
FALSE
Shroud Line Testing |  | 2. Mid |  |  | Order some eye bolts, set up Hesse date or ask MSE
Procedures review | Vehicle | 1. High |  |  |  | 2025-09-04 | 2025-09-05 | Manank Hemalkumar Doshi | TRUE
Determine motor | Vehicle | 1. High |  |  |  | 2025-09-04 | 2025-09-08 | Anton Vladimir Bogak Elise Jiaxin Fan | TRUE
Shopping list for solid demo V1 | Research | 1. High |  |  |  | 2025-09-04 | 2025-09-08 | Elise Jiaxin Fan | TRUE
Test article CAD | Vehicle | 1. High | Design the instron test plate for the u-bolts and eye bolts |  |  | 2025-09-04 | 2025-09-08 | Daniel Wiley Richards | TRUE
Lines diagram | Vehicle | 1. High |  |  |  | 2025-09-04 | 2025-10-01 | Laura Jane Wong | TRUE
Determine Shockloading | Vehicle | 1. High | Run calculations for chosen recovery methods |  | Create new shockloading calculator, select drogue/main | 2025-09-15 | 2025-10-05 | Manank Hemalkumar Doshi | TRUE
Component Selection SD2 | Vehicle | 1. High | Determine components for SD2 | [5 empty] | TRUE
DR: Avbay Annulus Design | [8 empty] | FALSE
Alpine Butterfly Knot Strength Test | Testing | 1. High |  |  |  | 2025-09-20 | 2025-10-05 | Elise Jiaxin Fan | FALSE | Fall25 Shock Cord Loop Strength Testing Procedures

## Copy of Tasks
TASK | CATEGORY | Column 3 | DESCRIPTION | PARAMETERS | ACTION ITEMS | START DATE | END DATE | RESPONSIBLE ENGINEER | DONE | WORKING LINK/ UPDATES/SOPs | REQUIRED HARDWARE/FACILITIES/APPROVALS
AV Bay Integration |  |  | - fix issues - write real integration procedures
Diagrams |  |  | make real harness and deployment diagrams
CADmaster |  |  | finalize bulkhead radial bolt, camera, vent hole placements, solid demo holes, fix tube lengths
Scale LE3 |  |  | for funsies
Weekend Prep |  |  | full ground test with ematches through BLE v2 and motherboard
Integration Procedures |  |  | write full recovery integration procedures
nut retainer designs |  |  | design a good nut retainer
to print
nut retainer
rail lug
tube 3 universal jig
tube 9 universal jig
tube 10 universal jig
Shroud Line Testing |  | 2. Mid |  |  | Order some eye bolts, set up Hesse date or ask MSE
DR: Avbay Annulus Design | [8 empty] | FALSE
Alpine Butterfly Knot Strength Test | Testing | 1. High |  |  |  | 2025-09-20 | 2025-10-05 | Elise Jiaxin Fan | FALSE | Fall25 Shock Cord Loop Strength Testing Procedures

## Report
Report | CATEGORY | Column 3 | DESCRIPTION | PARAMETERS | ACTION ITEMS | START DATE | END DATE | RESPONSIBLE ENGINEER | DONE | WORKING LINK/ UPDATES/SOPs | REQUIRED HARDWARE/FACILITIES/APPROVALS
Annotated Recovery Diagram | Vehicle | 1. High
Avionics Wiring Diagrams | Vehicle | 1. High
Main/Drogue Chute Deployment Energy | Vehicle | 1. High
Main/Drogue Shock Cord Equivalent Stiffness | Vehicle | 1. High | 1/2" Tubular kevlar from MAC Performance or Fruitychutes
Shroud Line Testing |  | 2. Mid |  |  | Order some eye bolts, set up Hesse date or ask MSE
DR: Avbay Annulus Design | [8 empty] | FALSE
Alpine Butterfly Knot Strength Test | Testing | 1. High |  |  |  | 2025-09-20 | 2025-10-05 | Elise Jiaxin Fan | FALSE | Fall25 Shock Cord Loop Strength Testing Procedures

## Agile Tasks
Task ID | Epic | Task | Owner (RE) | Points (# Days) | Date | Status | AC | Notes
VEH-3 | Vehicle | Chute Reefing | Laura, Chloe | 5 | 2025-11-10 | FALSE | Reef a chute
AVB-2 | Avbay | Flight Sim Program | Elise, Anton | 8 | 2025-11-13 | FALSE | Create a flight sim program that can decode blue raven quaternions into plottable data accurately | Check yaw math, pitch and roll check out. See if it's possible to animate the trajectory as well
AVB-3 | Avbay | Avbay Test Fit | Anton | 1 | 2025-11-03 | TRUE | Integrate all electronics and cases onto avbay | Some changes made to CAD
CQ-1 | Crimp Quality |  |  | 1 | 2025-11-03 | FALSE
FALSE
FALSE
VEH-1 | Vehicle | Lines Diagram | Laura, |  |  | FALSE
AVB-1 | Avbay | Weekend Blue Raven Testing Analyzation | Elise, | 1 | 2025-11-03 | FALSE | Finish analyzing weekend ground testing data
AVB-4 | Avbay | Avbay Cad Finalized | Anton | 1 | 2025-11-03 | TRUE | Finish the avbay cad | Just battery case resize and thats it
LC-1 | Line Cutter Confidence | Confidence Numbers | Chloe, Rebekah | 1 | 2025-11-03 | FALSE | Calculate how many tests for 99% Confidence, 99% Reliability (check SSEP2 Progress Reports) | Fa25 Line Cutter Confidence Calcs/Results
LC-2 | Line Cutter Confidence | Testing Setup | Chloe, Rebekah | 1 | 2025-11-03 | FALSE | Design a test for line cutters to simulate in-flight conditions before deployment, make new SOPs to match typical format | Line Cutter Testing - Google Docs
UB-1 | Ubolt Testing | Thread Tearout | Jocelyn | 1 | 2025-11-03 | FALSE | Calculate the tearout load required to strip the chosen U-bolts and eyebolts from their nuts, do research if people have Instron tested McMaster hardware before and what FOS should be, research how other teams validate U-bolts | Fall25 U-Bolt Testing Procedures Fa25 U-bolt Testing Calcs/Results
UB-2 | Ubolt Testing | Testing Setup Simulation | Jocelyn | 1 | 2025-11-03 | FALSE | Use calculated tearout load to FEA testing setup in Onshape, determine if FOS > 2 for 1/4" aluminum plate | Onshape > Airframe > Testing
RB-1 | Radial Bulkhead | Fiberglass Tearout | Angelo, | 1 | 2025-11-03 | FALSE | Ask airframe for/redo calculations/research of how much force 1 bolt requires to shear through fiberglass tubes | Fa25 Radial Bulkhead Testing
RB-2 | Radial Bulkhead | # Radial Screws | Angelo, | 1 | 2025-11-03 | FALSE | Use calculated tearout load from U-bolt calculations to determine how many airframe screws are required for FOS > 2 | Fastener Strength Calculator IREC 2022-2023
RB-3 | Radial Bulkhead | Bulkhead Design | Angelo, | 1 | 2025-11-03 | FALSE | Determine if areas of bulkhead could be reduced/pocketed from initial thickness and can still provide same strength
SC-1 | Shockcord | Splicing Testing | Laura, | 1 | 2025-11-03 | FALSE | Splice and sew a section of 1/4" Shockcord to qualitatively test splicing vs sewing | Fa25 Loop Strength Testing Calcs/Results
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
PCH-01 | Parachute | Shockloading model | Manank | 3 |  | FALSE | Fully worked out mathematical model ready to present to team | Fully worked mathematical and geometric model accounting for inertial loading, precessional motion, lag time, inflation, hyperelasticty, etc.
AVB-01 | Avbay | Avbay removable bulkhead redesign | Anton | 5 |  | FALSE | Design Review with substantive FOS on build | Need to consider tear out analysis, shear and axial loading, as well as failure modes in terms of installation failure and such
PCH-02 | Parachute | Finger trap vs bowline test | Elise | 8 |  | FALSE | Test Conducted with analysis ready to present to team | Build test plan (Instron setup), SOP writeup, run preliminary pulls.
PCH-03 | Parachute | Quicklink & soft link strength test prep | Elise | 8 |  | FALSE | Test matrix + BOM. | Collect hardware, define load cases, write SOP. need to do load case analysis of figuring out what is the expected loads of the system
PCH-04 | Parachute | Parachute inflation test | Anton + New Members | 3 |  | FALSE | Test Conducted with analysis ready to present to team | Run to inflate the 120, 36, 48, and 60 for more data for future equations
PCH-05 | Parachute | Parachute Bag | Laura | 5 |  | FALSE | Need Design v1 with analysis to present to team | Source Nomex, create scaled pattern, prototype sew. Need to consider freestream instances and load bearing stress rises, materials and sewing techniques need to considered in regards to that
PCH-06 | Parachute | Lines Diagram | Laura | 5 |  | FALSE | Need to do a team review with Diagram v1 | Build recovery lines diagram linking hardware loads to vehicle structure. Need to also conduct knot analysis and failure point/node analysis
AVB-02 | Avbay | Recovery Wiring Diagram | Daniel | 5 |  | FALSE | Present wiring connections v1 for team review | Draft wiring diagram for Fluctus + Featherweight GPS + altimeters. Do electrical connections analysis
AVB-03 | Avbay | Flight Computer Integration | Anton | 5 |  | FALSE | Test Writeup on the test results | Bench test Fluctus + Featherweight GPS lock.
SD2-01 | SD2 | Component Selection SD2 | Anton | 5 |  | FALSE | Determine proper sizes for components | Want: Bulkhead sizes, airframe size, U-bolt size, threaded rod size
BKD-01 | Bulkhead | Test Article CAD | Daniel | 1 |  | FALSE | Model and FEA the test articles and mounting plates for instron | Must be able to hold u bolts and eye bolts on same mount
PCH-07 | Parachute | Order Line Cutters | Elise, Anton | 1 |  | FALSE
SD2-02 | SD2 | SD2 Camera Mounts | Anton, ____ | 5 |  | FALSE | Make camera mount | Directly part of the avionics bay, camera lens should sit nearly flush with the
AVB-04 | SD2 | Avionics Tests | Anton, Daniel, Jocelyn, Angelo, Chloe | 3 |  | FALSE | Test GPS lock, blue raven status (and connectivity), Fluctus, and new batteries
| SD2 | Hot Sauce Mount | Angelo | 8 |  | FALSE
| Parachute | Shock cord splicing | Jocelyn, Laura |  |  | FALSE
| Parachute | Chute Patching | Laura |  |  | FALSE
| SD2 | Bulkhead sizing/holes | Rebecca, Chloe | 5 |  | FALSE
| SD2 | Line Cutters SOP | Anton | 3 |  | FALSE
Alpine Butterfly Knot Strength Test | Testing | 1. High |  |  |  | 2025-10-05 | Elise Jiaxin Fan | FALSE

## 1) Shockloading Calc
Parachute | Diameter (in) | Deployment Altitudes (ft AGL) | Deployment Velocity (ft/s) | Terminal Velocity (ft/s) | Shock Load (lbf)
Small Drogue | 48 | 10000 | 100 | 90.1 | 477
Big Drogue | 60 | 6000 | 90.1 | 59.9 | 914
Small Main | 96 | 3000 | 59.9 | 36.4 | 896
Big Main | 120 | 1200 | 36.4 | 24.3 | 530
Total Rocket Mass: 100.00 kg (220.5 lbs)
Apogee: 10,000 feet
Initial horizontal velocity: 100 ft/s
--- PARACHUTE 1 (48" SMAll-DROGUE) ---
Deployment altitude: 10,000 feet
Deployment time: 1.8 seconds
Velocity 0.1s after deployment:
Vertical: 3.3 ft/s
Horizontal: 99.7 ft/s
Total: 99.8 ft/s
Velocity after full deployment:
Vertical: 30.6 ft/s
Horizontal: 73.4 ft/s
Total: 79.5 ft/s
Maximum shock loading: 477 lbf
--- PARACHUTE 2 (60" BIG-DROGUE at 5000ft) ---
Deployment altitude: 6,000 feet
Deployment time: 1.8 seconds
Velocity at deployment:
Vertical: 90.1 ft/s
Horizontal: 20.3 ft/s
Total: 92.3 ft/s
Velocity after full deployment:
Vertical: 61.4 ft/s
Horizontal: 20.3 ft/s
Total: 64.7 ft/s
Maximum shock loading: 914 lbf
--- PARACHUTE 3 (96" SMALL-MAIN at 3000ft) ---
Deployment altitude: 3,000 feet
Deployment time: 2.3 seconds
Velocity at deployment:
Vertical: 59.9 ft/s
Horizontal: 24.6 ft/s
Total: 64.8 ft/s
Velocity after full deployment:
Vertical: 35.7 ft/s
Horizontal: 24.9 ft/s
Total: 43.5 ft/s
Maximum shock loading: 896 lbf
--- PARACHUTE 4 (120" MAIN at 1200ft) ---
Deployment altitude: 1,200 feet
Deployment time: 2.3 seconds
Velocity at deployment:
Vertical: 36.4 ft/s
Horizontal: 27.2 ft/s
Total: 45.4 ft/s
Velocity after full deployment:
Vertical: 24.6 ft/s
Horizontal: 27.2 ft/s
Total: 36.7 ft/s
Maximum shock loading: 530 lbf
--- LANDING ---

## 2) Radial Bolt Calcs
Outer Diameter | Inner Diameter | Thickness (in) | Thickness (mm) | Bolt Size (mm) | Shear Area (mm^2) | # Bolts | Force (N) | Force (kN) | Force (lbf)
6.17 | 5.82 | 0.175 | 4.445 | 5 | 22.225 | 8 | 35560 | 35.56 | 7994.6043
6.17 | 5.82 | 0.175 | 4.445 | 8 | 35.56 | 8 | 56896 | 56.896 | 12791.3669
6.17 | 5.82 | 0.175 | 4.445 | 5 | 22.225 | 4 | 17780 | 17.78 | 3997.3022
6.17 | 6 | 0.085 | 2.159 | 5 | 10.795 | 8 | 17272 | 17.272 | 3883.0935
6.17 | 6 | 0.085 | 2.159 | 6 | 12.954 | 8 | 20726.4 | 20.7264 | 4659.7122
6.17 | 6 | 0.085 | 2.159 | 7 | 15.113 | 8 | 24180.8 | 24.1808 | 5436.3309
6.17 | 6 | 0.085 | 2.159 | 8 | 17.272 | 8 | 27635.2 | 27.6352 | 6212.9496

## 3) Component Selection
Component | Force Rating (lbf) | Max Expected Force (lbf) | FOS | Analysis
Radial Bulkhead | 7994 | 914 | 8.7462 | Calcs, shear force from radial bulkhead testing
U-Bolt | 4000 | 914 | 4.3764 | U-bolt testing, at least as strong as rating
Quicklink | 7879 | 914 | 8.6204 | Quick link testing

## Packing Volumes
Diameter (in) | Radius (in) | Area (in^2) |  | 1.5932
5.83 | 2.915 | 26.6948 |  |  | 0.1 oz/in^3 |  | 3
ALULA | Tube Length (in) | Volume (in^3) | Shockcord (ft) | Parachute (in) | Parachute Mass (oz) | Shockcord Pack Length (in) | Shockcord Pack Volume (in^3) | Parachute Pack Volume (in^3) | Parachute Packing Density (oz/in^3)
Main | 15 | 400.4223 | 40 | 120 | 36 | 6 | 160.1689 | 240.2534 | 0.14984
ALULA | Tube Length (in) | Volume (in^3) | Shockcord (ft) | Parachute (in) | Parachute Mass (oz) | Shockcord Pack Length (in) | Shockcord Pack Volume (in^3) | Parachute Pack Volume (in^3) | Parachute Packing Density (oz/in^3)
Drogue | 13 | 347.0327 | 60 | 48 | 7.5 | 9 | 240.2534 | 106.7793 | 0.070238
Excalibur | Tube Length (in) | Volume (in^3) | Shockcord (ft) | Parachute (in) | Parachute Mass (oz) | Shockcord Pack Length (in) | Shockcord Pack Volume (in^3) | Parachute Pack Volume (in^3) | Parachute Packing Density (oz/in^3)
Main | 18 | 480.5068 | 45 | 84 | 19 | 5 | 133.4741 | 347.0327 | 0.05475
Excalibur | Tube Length (in) | Volume (in^3) | Shockcord (ft) | Parachute (in) | Parachute Mass (oz) | Shockcord Pack Length (in) | Shockcord Pack Volume (in^3) | Parachute Pack Volume (in^3) | Parachute Packing Density (oz/in^3)
Drogue | 8.5 | 226.906 | 55 | 36 | 5 | 7 | 186.8637 | 40.0422 | 0.12487
Caldera | Tube Length (in) | Volume (in^3) | Shockcord (ft) | Parachute (in) | Parachute Mass (oz) | Shockcord Pack Length (in) | Shockcord Pack Volume (in^3) | Parachute Pack Volume (in^3) | Parachute Packing Density (oz/in^3)
Sustainer | 11.75 | 313.6641 | 73.6 | 84, 36 | 24 | 8.5 | 226.906 | 86.7582 | 0.27663
Caldera | Tube Length (in) | Volume (in^3) | Shockcord (ft) | Parachute (in) | Parachute Mass (oz) | Shockcord Pack Length (in) | Shockcord Pack Volume (in^3) | Parachute Pack Volume (in^3) | Parachute Packing Density (oz/in^3)
Booster | 9.5 | 253.6008 | 32.9 | 60, 36 | 15.9 | 4 | 106.7793 | 146.8215 | 0.10829
Really | Tube Length (in) | Volume (in^3) | Shockcord (ft) | Parachute (in) | Parachute Mass (oz) | Shockcord Pack Length (in) | Shockcord Pack Volume (in^3) | Parachute Pack Volume (in^3) | Parachute Packing Density (oz/in^3)
Terrible Idea |  | 100 | 40 | 60, 12 | 7 |  | 50 | 50 | 0.14
Shockcord Pack Density (ft/in)
6.6667 |  |  | Shockcord Pack Density (ft/in) | 7.5 |  | Parachute (in) | 60
6.6667 |  |  | Shockcord Length | 60 |  | Parachute Mass (oz) | 8
|  |  | Shockcord Pack Density (ft/in^3) | 0.03746 |  | Parachute Pack Density (oz/in^3) | 0.1
7.8571 |  |  | Shockcord Pack Length (in) | 8 |  | Parachute Pack Volume (in^3) | 80 | 2.9968
8.6588 |  |  | Shockcord Pack Volume (in^3) | 213.5586 |  | Total Bay Volume (in^3) | 293.5586
8.225 | [5 empty] | Coupler Length Needed (in^3) | 0
Average
7.6149
|  |  | Shockcord Pack Density (ft/in) | 7.5 |  | Parachute (in) | 60, 48
|  |  | Shockcord Length | 100 |  | Parachute Mass (oz) | 18.4 | 109
|  |  | Shockcord Pack Density (ft/in^3) | 0.03746 |  | Parachute Pack Density (oz/in^3) | 0.1
|  |  | Shockcord Pack Length (in) | 13.3333 |  | Parachute Pack Volume (in^3) | 184
|  |  | Shockcord Pack Volume (in^3) | 355.9309 |  | Total Bay Volume (in^3) | 539.9309
[6 empty] | Total Bay Length (in) | 20.2261

## 4) Ejection Charges & Shear Pin
INPUTS | Length (In)
Recovery bay inner diameter | 6 |  | cone volume = 600
Main space length | 21.22 |  | 21.2207
Drogue space length | 27.75
6-32 nylon screw shear strength | 75-114 lbs
Drogue ~1.5 g charge (charge well) | PSI VALUE | RECOMMENDED BP AMOUNT (g) | FORCE ON BULKHEAD (lbs) | # OF 6-32 SHEARED AT MIN STRENGTH | # OF 6-32 SHEARED AT MAX STRENGTH
| 10 | 3.85 | 282.6 | 4 | 2
| 15 | 5.99 | 423.9 | 6 | 4
| 20 | 7.99 | 565.2 | 8 | 5
| 25 | 9.99 | 706.5 | 9 | 6
Main ~6 g charge | PSI VALUE | RECOMMENDED BP AMOUNT (g) | FORCE ON BULKHEAD (lbs) | # OF 6-32 SHEARED AT MIN STRENGTH | # OF 6-32 SHEARED AT MAX STRENGTH
| 10 | 3.06 | 282.6 | 4 | 2
| 15 | 4.58 | 423.9 | 6 | 4
| 20 | 6.11 | 565.2 | 8 | 5
| 25 | 7.64 | 706.5 | 9 | 6
SOURCES
https://rocketrycalculator.com/rocketry-calculator/bp-estimator/
https://www.insanerocketry.com/blackpowder.html
https://www.feretich.com/Rocketry/Resources/shearPins.html
https://leederville.net/rocket/index.php/2017/10/21/shear-pin-calculations/
https://www.mide.com/air-pressure-at-altitude-calculator
Alula Shear Pin Calculations

## 5) Power Budget
Part | Qty | Supply Current Per Device (A) | Supply Voltage per Component (V) | Power Subtotal (W) | Time (s) | Total Energy (Wh) | Total Power Capability (mAh)
Blue Raven Altimeters | 2 | 0.0225 | 3.3 | 0.07425 | 21600 | 0.4455 | 135
Featherweight GPS | 1 | 0.086 | 3.3 | 0.2838 | 21600 | 1.7028 | 516
Backup Altimeter: EasyMega |  | 0.15 | 3.3 | 0.495 | 21600 | 2.97 | 900
Backup GPS: TeleGPS |  | 0.15 | 3.3 | 0.495 | 21600 | 2.97 | 900
Bluetooth Switch | 1 | 0.0128 | 3.3 | 0.04224 | 21600 | 0.25344 | 76.8
Efficiency: | 100
Total Current (A) | 0.131
Total Power (W) | 0.35805
Total Power Input (W) | 0.35805 | Note: assumes 100% efficiency and all devices on simultaneously
Total Energy (W-h) | 2.1483
Total Power Capacity (mAh) | 651
Battery | Cost | Qty | Cost Per | mAh | Wh | Hours of Runtime (Blue Raven) | Hours of Runtime (Blue Raven + BLE Switch) | Hours of Runtime (GPS) | Hours of Runtime (GPS + BLE Switch) | Hours of Runtime (Backup: EasyMega) | Hours of Runtime (Backup: TeleGPS)
Amazon 1200mAh 30C | 27 | 5 | 5.4 | 1200 | 4.44 | 59.798 | 38.1149 | 15.6448 | 13.618 | 8.9697 | 8.9697
Altus Metrum 450mAh | 8.5 | 1 | 8.5 | 400 | 1.48 | 19.9327 | 12.705 | 5.2149 | 2.7548 | 2.9899 | 2.9899
Altus Metrum 850mAh | 10 | 1 | 10 | 850 | 3.145 | 42.3569 | 26.998 | 11.0817 | 5.854 | 6.3535 | 6.3535
Amazon 850mAh 25C | 22 | 5 | 4.4 | 850 | 3.145 | 42.3569 | 26.998 | 11.0817 | 37.2277 | 6.3535 | 6.3535
Amazon 600mAh 25C | 22 | 5 | 4.4 | 600 | 2.22 | 29.899 | 19.0574 | 7.8224 | 52.5568 | 4.4848 | 4.4848
Amazon 800mAh 25C | 24 | 6 | 4 | 800 | 2.96 | 39.8653 | 25.4099 | 10.4299 | 70.0758 | 5.9798 | 5.9798
Amazon 750mAh 25C | 19 | 5 | 3.8 | 750 | 2.775 | 37.3737 | 23.8218 | 9.778 | 65.696 | 5.6061 | 5.6061
Amazon 3000mAh 1C | 29 | 4 | 7.25 | 3000 | 11.1 | 149.4949 | 95.2871 | 39.1121 | 262.7841 | 22.4242 | 22.4242
Featherweight Blue Raven User Manual: Runs on a 180 mAh 1s LiPo for 8+ hours
180 mAh | = 22.5 mA
8 hours

## 9) Flight CONOPS Specs
|  | TIME (s) | TOTAL SPEED (ft/s) | ALTITUDE AGL (ft) | MACH | DISTANCE (ft) | DIRECTION
0 | Liftoff | 0 | 0 | 0 | 0 | 0 | Upwind
1 | Powered Flight | 0.346 | 101.6 | 16 |  | 1.4 | Upwind
| Max Velocity | 3.71 | 961.6 | 1833 |  | 255.5 | Upwind
2 | Motor Burnout/ Coast Start | 4.27 | 937.7 | 2236 |  | 341.4 | Upwind
3 | Apogee/ Drogue Deploy | 25.267 | 130 | 10836 |  | 3149 | Upwind
4 | Main Deploy | 178 | -61.05 | 1202 |  | 5.2 | Downwind
5 | Payload Deploy | 183 | -54.2 | 998 |  | -76.2 | Downwind
6 | Airframe Landing | 217.64 | 24.94 | 0 |  | -861.8 | Downwind
| ROCKETPY | TIME (s) | TOTAL SPEED (ft/s) | ALTITUDE AGL (ft) | MACH | DISTANCE (ft) | DIRECTION
7 | Payload Terminal* | [5 empty] | Downwind
8 | Payload Landing* | 233.163 | 15.84 | 0 |  | -840 | Downwind
*Payload specs
| FLIGHT SIMS CONDITIONS |  |  |  | VERSION NUMBER
| Windspeed | mph | 15 |  | RASaero | 1.2.1
| Standard Deviation | mph | 3 |  | Open Rocket | 1.2.1
| Turbulence | % | 13.2 |  | Spreadsheet Ork | ??
| Wind Direction | degrees | 90 |  | RocketPy | no version
| Temperature | F | 110
| Pressure | mbar | 871.4
| Lattitude | N | 32.9885
| Longitude | E | -106.9751
| Altitude | ft | 4872.1129
| Rail Length | m | 5.6
| Rail Angle | degrees | 4

## Inventory
Item | Qty | Shelf | Notes | Brand
IPA | 1 | Shipping Container | Move to flammables cabinet
Clear Gorilla Glue | 1 | Shipping Container | Move to flammables cabinet
Loctite | 1 | Shipping Container | Move to flammables cabinet
Gorilla glue gel | 1 | Shipping Container | Move to flammables cabinet
Graphite Lubricant | 1 | Shipping Container | Move to flammables cabinet
Red Sharpies | 3 | Recovery Bag
Big GPS Antennae | 2 | 7
Scissors | 1 | 6
Multimeter | 1 | 6
Whiteout tape | 1 | 6
Labelmaker | 1 | 6
Assorted star drive screw bits | 10 | 5
Cen-Tech Milligram Scale | 1 | 5 |  | Cen-Tech
Wireless Hot Glue Gun | 1 | 5 |  | GoGonova
Maxus Milligram Scale | 1 | 5 |  | Maxus
Plastic Vial Caps (Bag) | 1 | 5
7 mL Plastic Vial (Bag) | 1 | 5 |  | Hapy Shop
Fuzion Digital Scale | 1 | 5 |  | Fuzion
Metal Funnel Set | 1 | 5
Black Powder Volumetric Vial (Bag) | 1 | 5
Metal Cups | 10 | 5
6-32 x 3/4" Nylon Screw (Box) | 1 | 5
6-32 x 1/2" Nylon Screw (Box) | 1 | 5
6-32 x 1" Nylon Screw (Bag) | 1 | 5
Assorted Shear Pins / Shear Nuts | Box | 5
Zip Ties | 3 bag | 4
DT Gray Connectors | 4 | 4
Assorted Avbay Screws (M3) | Box | 4
Unthreaded rod | 2 | 4
600 mAh LiPo | 4 | 3
1200 mAh LiPo (1S) | 13 | 3 | 5 nonfunctional
1200 mAh LiPo (2S) | 2 | 3
Blue Raven Altimeter | 4 | 3 |  | Blue Raven
BLE Switch | 3 | 3
Featherweight GPS 5238 | 1 | 3 | Alive | Featherweight
Featherweight Blue Raven 1360 | 1 | 3 | Alive | Featherweight
Featherweight Blue Raven 1490 | 1 | 3 | Alive | Featherweight
Featherweight Blue Raven 0843 | 1 | 3 | Alive | Featherweight
Featherweight Blue Raven 1358 | 1 | 3 |  | Featherweight
Blue Raven Extensions | 6 | 3 |  | Additive Aerospace
Antistatic Bag | 2 | 3
Eggtimer Quantum (unassembled) | 1 | 3 |  | Eggtimer
Altus Metrum TeleBT 3773 | 1 | 3 |  | Altus Metrum
Eggtimer Eggfinder TX | 1 | 3 |  | Eggtimer
Eggtimer Eggfinder Ground Station | 2 | 3 |  | Eggtimer
PerfectFlite Stratologer Altimeter | 4 | 3 |  | PerfectFlite
PerfectFlite Stratologger Data Cable | 1 | 3 |  | PerfectFlite
9V Battery Clip | 1 | 3
CP2102 Module USB to TTL | 1 | 3
Palm Beach Robotics Screw Switch | 1 | 3 |  | Palm Beach Robotics
Eggtimer WiFi Switch | 4 | 3 |  | Eggtimer
Featherweight GPS Groundstation | 1 | 3 |  | Featherweight
Featherweight Blue Raven 1359 | 1 | 3 | Alive
Featherweight Blue Raven 1491 | 1 | 3 | Alive
Featherweight Blue Raven 1021 | 1 | 3 | Dead
Recovery Motherboard | 2 | 3
Payload actuator boards | 2 | 3
Flight Computer V5 | 1 | 3
DT Connector Tool | 5 | 3
Featherweight GPS 4769 | 1 | 3 | Dead
JST XH 2.54mm Connectors | 40 | 3
Terminal Blocks | 5 | 3
Terminal Connectors | 7 | 3
Terminal Connector Sheaths | 17 | 3
EasyMega | 4 | 3
TeleGPS | 5 | 3
Easytimer | 1 | 3
Eggtimer | 1 | 3
12-Gague Crimp Connectors | 100 | 3
9V Batteries | 10 | 3
JST PH Connectors | 50 | 3
JST PH Wires | 10 | 3
Wired Screw Switches | 3 | 3
JST XH Wires | 10 | 3
Live Video Antenna | 1 | 3
Assorted JST XH Wires | 6 | 3
BLE Switch V3 | 1 | 3 | Needs new connector
Assorted Terminal Blocks | Bag | 3
Ballast plates | 18 | 2
Backup M5 Screws | 1 bag | 2
M4 Screws | 15 | 2
Live Video Heatsink | 1 | 2
Small U-bolts and Quicklinks | Box | 2
Tender Descender | 4 | 2
Avbay Bulkhead Upper | 1 | 2
Unknown Heatsink | 1 | 2
Camera shroud | 1 | 2
Avbay 1 inch lower standoffs + U-plate | 2,1 | 2
GX12 connector | 14 | 1
Altus Metrum Teledongle | 1 | 1 |  | Altus Metrum
1/4" Hex Shank Power Wing Nut Driver Kit | 2 | 1 |  | WIMNISV
Tinder Rocketry Peregrine Kit | 2 | 1 |  | Tinder Rocketry
Bridge Cable Kit | 1 | 1
Singer Hand Needle 45PCS | 1 | 1 |  | Singer
USB LiPo Charger | 3 | 1
Black Nylon Upholstery Thread | 1 | 1 |  | Coats & Clark
DT Connector Tool | 1 | 1 |  | TE Connectivity
Washer 10mm | 75 | 1
White Elastic Spool | 1 | 1
3d printed spacers | 12 | 1
1 inch standoffs | 15 | 1
Miscellaneous small screws | 1 bag | 1
M3x8 screws | 1 bag | 1
Plastic 5mm spacers | 2 bags | 1
U bolts 1 inch | 2 | 1
1/4-20 U-Bolt | 5 | 1 |  | Chicago Hardware
Jumbo Cotton Ball Bag | 1 | 1 |  | Walgreens
1/4" x 1-1/8" x 2" U-Bolt | 8 | 1
5/16" x 2" x 3" U-Bolt | 13 | 1
880lbs Quick Link | 12 | 1
500lbs Swivel | 4 | 1 | Apogee Components
Unknown Swivel | 1 | 1
1/4" x 1 1/2" Reefing Ring | 4 | 1
Misc Eye Bolts (Bag) | 1 | 1
220lbs Quick Links | 11 | 1
1/2"-13 x 3" U-Bolt | 2 | 1
2500 lbs Quick Link | 1 | 1
1000lbs Quick Link | 1 | 1
1760lbs Quick Link | 3 | 1
Misc Carabiner | 4 | 1
Unknown Quick Link | 9 | 1
Unknown U-Bolt | 3 | 1
Shear pins
Box of small screwdrivers
Label maker
GX12 Connectors | 6
Parachutes
Ringsail 48" (heavily damaged in shroud lines but reparable) | 1
36" Ringsail (good) | 1
144" Ultralight PDA | 1
84" Standard PDA (cooked) | 1
120" Standard PDA (repairable) | 1
36" Standard PDA (one new and one old) | 2
60" Standard PDA (little to no damage) | 1
48" Standard PDA (1 repairable and 1 good) | 2
30" Standard PDA (bridal damage) | 1
60" Parachute bag (4.5" * 9") | 1
48" parachute bag (4" * 9") | 1
Tender descender bag | 3
84" parachute bag (5" * 9") | 3
120" parachute bag (7" * 11") (mostly scrap) | 1
120" parachute bag (9.5" * 11") | 1
Shock cord testing fixture | 4
Shock packs | 2
36" parachute bag | 1
Fireballs | 2
60" Standard PDA (needs repair) | 1

## 2) 3 Parachute Shockloading
| Options | Main Size | Drogue Size | Main Shock load | Drogue Shock Load | Main Descent | Drouge Descent |  |  |  |  | Key: | Boxes in yellow are user inputs |  | Boxes in green are calculated intermediaries | Boxes in blue are outputs
| 1 | 168 | 72 | 499.7119 | 793.2579 | 43.1238 | 67.3149 | [5 empty] | Projected Diameter/Area: listed diameter of the parachute, and area calculated from listed diameter, which represents the 2D area of the parachute when looking down the velocity axis |  | Drag coefficient: Dimensionless, positive number characteristic to the parachute and describing how much drag per unit area the shape of the parachute yields, symbol is Cd (need to look it up, a reference is provided below) | Shock loading coefficient: Dimensionless, positive number characteristic to the parachute and describing the manner in which the parachute opens, symbol is Cx (need to look it up, a reference is provided below) | Shock reduction factor: Dimensionless number between 0 and 1 describing the dampening due to the mass of the rocket, symbol is X, higher is heavier, 1 assumes infinite mass (safe approximation)
| 2 | 168 | 60 | 1646.4 | 771.1254 | 19.8302 | 63.6659 | [5 empty] | Infinite mass: The approximation of setting the shock reduction factor to 1, which assumes the rocket does not slow down during parachute deployment |  | Pflanz method reduction factor: The shock reduction factor as calculated using the Pflanz method, described below | Stage dry weight: The mass of the relevant rocket stage with engine hardware but no propellant onboard | AMSL: altitude "above mean sea level" (as opposed to "above ground level")
| 3 | 168 | 48 | 2940 | 493.5203 | 21.1994 | 85.0772
| 4 | 168 | 36 | 5226.6667 | 277.6051 | 21.1994 | 113.4362 | [5 empty] | Parachute Type: |  | Drag Coefficient: | Shock Loading Coefficient: | Pflanz method to be added later
| 5 | 144 | 72 | 960 | 1110.4206 | 24.6583 | 56.7181 | [5 empty] | Hemispherical parachute from FruityChutes (sometimes called "elliptical"): |  | 1.6 (using FruityChutes' projected area) | 1.6
| 6 | 144 | 60 | 1382.4 | 771.1254 | 24.6583 | 68.0617 | [5 empty] | Pull-down apex parachute from FruityChutes (marketed as their "Iris" parachutes): |  | 2.2 (using FruityChutes' projected area) | ~1.5-1.8 (1.3 for disc-gap-band, 1.4 for annular, 1.6 for hemispherical, the author is extrapolating that 1.5 could be a fair estimate for PDA parachutes, with this exception: PDAs have an incredibly high D_p/D_0 ratio and hence a very high Cd; one can extrapolate from this that the shock load factor should also be very high, quite possibly higher than an annular or hemispherical...) | Source: chrome-extension://efaidnbmnnnibpcajpcglclefindmkaj/https://apps.dtic.mil/sti/tr/pdf/ADA247666.pdf
| 7 | 144 | 48 | 2160 | 493.5203 | 24.6583 | 85.0772
| 8 | 144 | 36 | 3840 | 277.6051 | 24.6583 | 113.4362
| 9 | 120 | 72 | 666.6667 | 1110.4206 | 29.59 | 56.7181
| 10 | 120 | 60 | 960 | 771.1254 | 29.59 | 68.0617
| 11 | 120 | 48 | 1500 | 493.5203 | 29.59 | 85.0772
| 12 | 120 | 36 | 2666.6667 | 277.6051 | 29.59 | 113.4362
Option 1 Main: 120" PDA Small Main: 84" PDA Drogue: 60" PDA | [12 empty] | 2 | 2.5 | 3
Ground Altitude AMSL (ft): | 2050 | Ground Velocity at Drogue Deployment (ft/s): | 100 | Air Velocity at Main 1 Deployment (ft/s): | 60.3733 | Air Velocity at Main 2 Deployment (ft/s): | 24.4828 | Landing Air Velocity (ft/s): | 41.2266 |  |  |  | Minimum | Acceptable | Goal
Apogee AGL(ft): | 10000 | Drogue Projected Diameter (in): | 60 | Main 1 Projected Diameter (in): | 84 | Main 1 Projected Diameter (in): | 144 | Drogue Shock Load at Inf. Mass (lbf): | 793.2579 |  |  |  | 1586.5158 | 1983.1448 | 2379.7737
Main 1 Deployment Altitude AGL (ft): | 3000 | Drogue Projected Area (ft²): | 19.6349 | Main Projected Area (ft²): | 38.4845 | Main Projected Area (ft²): | 113.0972 | Drogue Shock Load with Reduction Factor (lbf): | 396.629
Main 2 Deployment Altitude AGL (ft): | 1200 | Drogue Drag Coeff: | 2.2 | Main Drag Coeff: | 2.2 | Main Drag Coeff: | 2.2 | Main Shock Load at Inf. Mass (lbf): | 499.7119 | Main Shock Load at Inf. Mass (lbf): | 241.5 |  | 999.4238 | 1249.2797 | 1499.1357
Stage Dry Weight (lbs): | 161 | Drogue Shock Loading Coeff: | 1.5 | Main Shock Loading Coeff: | 1.5 | Main Shock Loading Coeff: | 1.5 | Main Shock Load with Reduction Factor (lbf): | 249.8559 | Main Shock Load with Reduction Factor (lbf): | 120.75 |  |  | lbf | Newtons
Air Density at Apogee (slug/ft^3): | 0.0016451 | Drogue Shock Reduction Factor: | 0.5 | Main Shock Reduction Factor: | 0.5 | Main Shock Reduction Factor: | 0.5 | Kinetic Energy on Impact (ft-lbf): | 4252.515 |  |  |  |  | 793.2579 | 3528.587
Air Density at Main 1 Deployment (slug/ft^3): | 0.0020451 | Max Terminal Velocity Under Drogue (ft/s): | 67.3149 | Main Terminal Velocity (ft/s): | 43.1238 | Main Terminal Velocity (ft/s): | 24.4828 | Drift Distance (ft): | 4109.7681 |  |  |  |  | 499.7119 | 2222.8292
Air Density at Main 2 Deployment (slug/ft^3): | 0.002159 | Descent Time (s): | 186.8076
Air Density at Ground (slug/ft^3): | 0.0022377
Wind Speed (ft/s): | 22
Option 1 Main: 120" PDA Small Main: 84" PDA Drogue: 60" PDA | GLENNIS
Ground Altitude AMSL (ft): | 2050 | Ground Velocity at Drogue Deployment (ft/s): | 100 | Air Velocity at Main 1 Deployment (ft/s): | 70.8672 | Air Velocity at Main 2 Deployment (ft/s): | 28.5401 | Landing Air Velocity (ft/s): | 54.1996
Apogee AGL(ft): | 10000 | Drogue Projected Diameter (in): | 24 | Main 1 Projected Diameter (in): | 30 | Main 2 Projected Diameter (in): | 58 | Drogue Shock Load at Inf. Mass (lbf): | 43.2686
Main 1 Deployment Altitude AGL (ft): | 3000 | Drogue Projected Area (ft²): | 3.1416 | Small Main Projected Area (ft²): | 4.9087 | Main Projected Area (ft²): | 18.3478 | Drogue Shock Load with Reduction Factor (lbf): | 21.6343
Main 2 Deployment Altitude AGL (ft): | 1200 | Drogue Drag Coeff: | 0.75 | Main Drag Coeff: | 0.75 | Main Drag Coeff: | 0.75 | Main Shock Load at Inf. Mass (lbf): | 29.9394
Stage Dry Weight (lbs): | 12.1 | Drogue Shock Loading Coeff: | 1.5 | Main Shock Loading Coeff: | 1.5 | Main Shock Loading Coeff: | 1.5 | Main Shock Load with Reduction Factor (lbf): | 14.9697
Air Density at Apogee (slug/ft^3): | 0.0016451 | Drogue Shock Reduction Factor: | 0.5 | Main Shock Reduction Factor: | 0.5 | Main Shock Reduction Factor: | 0.5 | Kinetic Energy on Impact (ft-lbf): | 552.3856
Air Density at Main 1 Deployment (slug/ft^3): | 0.0020451 | Max Terminal Velocity Under Drogue (ft/s): | 79.0154 | Main Terminal Velocity (ft/s): | 56.6938 | Main Terminal Velocity (ft/s): | 28.5401 | Drift Distance (ft): | 3353.8712
Air Density at Main 2 Deployment (slug/ft^3): | 0.002159 | Descent Time (s): | 152.4487
Air Density at Ground (slug/ft^3): | 0.0022377
Wind Speed (ft/s): | 22
Option 2 Main: 168" PDA Drogue: 60" PDA | [6 empty] | FOS: | 2 | 2.5 | 3
Ground Altitude AMSL (ft): | 2934 | Ground Velocity at Drogue Deployment (ft/s): | 100 | Air Velocity at Main Deployment (ft/s): | 55.5247 | Landing Air Velocity (ft/s): | 19.4766 | Minimum | Acceptable | Goal
Apogee AGL(ft): | 10000 | Drogue Projected Diameter (in): | 60 | Main Projected Diameter (in): | 168 | Drogue Shock Load at Inf. Mass (lbf): | 771.1254 | 1542.2508 | 1927.8135 | 2313.3762
Main Deployment Altitude AGL (ft): | 1200 | Drogue Projected Area (ft²): | 19.6349 | Main Projected Area (ft²): | 153.9379 | Drogue Shock Load with Reduction Factor (lbf): | 385.5627
Stage Dry Weight (lbs): | 140 | Drogue Drag Coeff: | 2.2 | Main Drag Coeff: | 2.2 | Main Shock Load at Inf. Mass (lbf): | 1646.4 | 3292.8 | 4116 | 4939.2
Air Density at Apogee (slug/ft^3): | 0.0015992 | Drogue Shock Loading Coeff: | 1.5 | Main Shock Loading Coeff: | 1.5 | Main Shock Load with Reduction Factor (lbf): | 823.2 |  | lbf | Newtons
Air Density at Main Deployment (slug/ft^3): | 0.0021025 | Drogue Shock Reduction Factor: | 0.5 | Main Shock Reduction Factor: | 0.5 | Kinetic Energy on Impact (ft-lbf): | 825.3153 | Drogue | 771.1254 | 3430.1367
Air Density at Ground (slug/ft^3): | 0.0021795 | Max Terminal Velocity Under Drogue (ft/s): | 63.6659 | Main Terminal Velocity (ft/s): | 19.8302 | Drift Distance (ft): | 4814.722 | Main | 1646.4 | 7323.5521
Wind Speed (ft/s): | 22 | Descent Time (s): | 218.851
Option 3 Main: 168" PDA Drogue: 48" PDA | [6 empty] | FOS: | 2 | 2.5 | 3
Ground Altitude AMSL (ft): | 2934 | Ground Velocity at Drogue Deployment (ft/s): | 100 | Air Velocity at Main Deployment (ft/s): | 74.198 | Landing Air Velocity (ft/s): | 20.8214 | Minimum | Acceptable | Goal
Apogee AGL(ft): | 10000 | Drogue Projected Diameter (in): | 48 | Main Projected Diameter (in): | 168 | Drogue Shock Load at Inf. Mass (lbf): | 493.5203 | 987.0405 | 1233.8007 | 1480.5608
Main Deployment Altitude AGL (ft): | 1200 | Drogue Projected Area (ft²): | 12.5664 | Main Projected Area (ft²): | 153.9379 | Drogue Shock Load with Reduction Factor (lbf): | 246.7601
Stage Dry Weight (lbs): | 160 | Drogue Drag Coeff: | 2.2 | Main Drag Coeff: | 2.2 | Main Shock Load at Inf. Mass (lbf): | 2940 | 5880 | 7350 | 8820
Air Density at Apogee (slug/ft^3): | 0.0015992 | Drogue Shock Loading Coeff: | 1.5 | Main Shock Loading Coeff: | 1.5 | Main Shock Load with Reduction Factor (lbf): | 1470 |  | lbf | Newtons
Air Density at Main Deployment (slug/ft^3): | 0.0021025 | Drogue Shock Reduction Factor: | 0.5 | Main Shock Reduction Factor: | 0.5 | Kinetic Energy on Impact (ft-lbf): | 1077.9628 | Drogue | 493.5203 | 2195.2875
Air Density at Ground (slug/ft^3): | 0.0021795 | Max Terminal Velocity Under Drogue (ft/s): | 85.0772 | Main Terminal Velocity (ft/s): | 21.1994 | Drift Distance (ft): | 3865.5147 | Main | 2940 | 13077.7715
Wind Speed (ft/s): | 22 | Descent Time (s): | 175.7052
Option 4 Main: 168" PDA Drogue: 36" PDA | [6 empty] | FOS: | 2 | 2.5 | 3
Ground Altitude AMSL (ft): | 2934 | Ground Velocity at Drogue Deployment (ft/s): | 100 | Air Velocity at Main Deployment (ft/s): | 98.9307 | Landing Air Velocity (ft/s): | 20.8214 | Minimum | Acceptable | Goal
Apogee AGL(ft): | 10000 | Drogue Projected Diameter (in): | 36 | Main Projected Diameter (in): | 168 | Drogue Shock Load at Inf. Mass (lbf): | 277.6051 | 555.2103 | 694.0129 | 832.8154
Main Deployment Altitude AGL (ft): | 1200 | Drogue Projected Area (ft²): | 7.0686 | Main Projected Area (ft²): | 153.9379 | Drogue Shock Load with Reduction Factor (lbf): | 138.8026
Stage Dry Weight (lbs): | 160 | Drogue Drag Coeff: | 2.2 | Main Drag Coeff: | 2.2 | Main Shock Load at Inf. Mass (lbf): | 5226.6667 | 10453.3333 | 13066.6667 | 15680
Air Density at Apogee (slug/ft^3): | 0.0015992 | Drogue Shock Loading Coeff: | 1.5 | Main Shock Loading Coeff: | 1.5 | Main Shock Load with Reduction Factor (lbf): | 2613.3333 |  | lbf | Newtons
Air Density at Main Deployment (slug/ft^3): | 0.0021025 | Drogue Shock Reduction Factor: | 0.5 | Main Shock Reduction Factor: | 0.5 | Kinetic Energy on Impact (ft-lbf): | 1077.9628 | Drogue | 277.6051 | 1234.8492
Air Density at Ground (slug/ft^3): | 0.0021795 | Max Terminal Velocity Under Drogue (ft/s): | 113.4362 | Main Terminal Velocity (ft/s): | 21.1994 | Drift Distance (ft): | 3227.2694 | Main | 5226.6667 | 23249.3716
Wind Speed (ft/s): | 22 | Descent Time (s): | 146.6941
Option 5 Main: 144" PDA Drogue: 72" PDA | [6 empty] | FOS: | 2 | 2.5 | 3
Ground Altitude AMSL (ft): | 2934 | Ground Velocity at Drogue Deployment (ft/s): | 100 | Air Velocity at Main Deployment (ft/s): | 49.3167 | Landing Air Velocity (ft/s): | 24.2916 | Minimum | Acceptable | Goal
Apogee AGL(ft): | 10000 | Drogue Projected Diameter (in): | 72 | Main Projected Diameter (in): | 144 | Drogue Shock Load at Inf. Mass (lbf): | 1110.4206 | 2220.8412 | 2776.0515 | 3331.2618
Main Deployment Altitude AGL (ft): | 1000 | Drogue Projected Area (ft²): | 28.2743 | Main Projected Area (ft²): | 113.0972 | Drogue Shock Load with Reduction Factor (lbf): | 555.2103
Stage Dry Weight (lbs): | 160 | Drogue Drag Coeff: | 2.2 | Main Drag Coeff: | 2.2 | Main Shock Load at Inf. Mass (lbf): | 960 | 1920 | 2400 | 2880
Air Density at Apogee (slug/ft^3): | 0.0015992 | Drogue Shock Loading Coeff: | 1.5 | Main Shock Loading Coeff: | 1.5 | Main Shock Load with Reduction Factor (lbf): | 480 |  | lbf | Newtons
Air Density at Main Deployment (slug/ft^3): | 0.0021152 | Drogue Shock Reduction Factor: | 0.5 | Main Shock Reduction Factor: | 0.5 | Kinetic Energy on Impact (ft-lbf): | 1467.2271 |  | 1110.4206 | 4939.3969
Air Density at Ground (slug/ft^3): | 0.0021795 | Max Terminal Velocity Under Drogue (ft/s): | 56.7181 | Main Terminal Velocity (ft/s): | 24.6583 | Drift Distance (ft): | 4861.4361 |  | 960 | 4270.2928
Wind Speed (ft/s): | 22 | Descent Time (s): | 220.9744
Option 6 Main: 144" PDA Drogue: 60" PDA | [6 empty] | FOS: | 2 | 2.5 | 3
Ground Altitude AMSL (ft): | 2934 | Ground Velocity at Drogue Deployment (ft/s): | 100 | Air Velocity at Main Deployment (ft/s): | 59.18 | Landing Air Velocity (ft/s): | 24.2916 | Minimum | Acceptable | Goal
Apogee AGL(ft): | 10000 | Drogue Projected Diameter (in): | 60 | Main Projected Diameter (in): | 144 | Drogue Shock Load at Inf. Mass (lbf): | 771.1254 | 1542.2508 | 1927.8135 | 2313.3762
Main Deployment Altitude AGL (ft): | 1000 | Drogue Projected Area (ft²): | 19.6349 | Main Projected Area (ft²): | 113.0972 | Drogue Shock Load with Reduction Factor (lbf): | 385.5627
Stage Dry Weight (lbs): | 160 | Drogue Drag Coeff: | 2.2 | Main Drag Coeff: | 2.2 | Main Shock Load at Inf. Mass (lbf): | 1382.4 | 2764.8 | 3456 | 4147.2
Air Density at Apogee (slug/ft^3): | 0.0015992 | Drogue Shock Loading Coeff: | 1.5 | Main Shock Loading Coeff: | 1.5 | Main Shock Load with Reduction Factor (lbf): | 691.2 |  | lbf | Newtons
Air Density at Main Deployment (slug/ft^3): | 0.0021152 | Drogue Shock Reduction Factor: | 0.5 | Main Shock Reduction Factor: | 0.5 | Kinetic Energy on Impact (ft-lbf): | 1467.2271 | Drogue | 771.1254 | 3430.1367
Air Density at Ground (slug/ft^3): | 0.0021795 | Max Terminal Velocity Under Drogue (ft/s): | 68.0617 | Main Terminal Velocity (ft/s): | 24.6583 | Drift Distance (ft): | 4207.6801 | Main | 1382.4 | 6149.2216
Wind Speed (ft/s): | 22 | Descent Time (s): | 191.2582
Option 7 Main: 144" PDA Drogue: 48" PDA | [6 empty] | FOS: | 2 | 2.5 | 3
Ground Altitude AMSL (ft): | 2934 | Ground Velocity at Drogue Deployment (ft/s): | 100 | Air Velocity at Main Deployment (ft/s): | 73.975 | Landing Air Velocity (ft/s): | 24.2916 | Minimum | Acceptable | Goal
Apogee AGL(ft): | 10000 | Drogue Projected Diameter (in): | 48 | Main Projected Diameter (in): | 144 | Drogue Shock Load at Inf. Mass (lbf): | 493.5203 | 987.0405 | 1233.8007 | 1480.5608
Main Deployment Altitude AGL (ft): | 1000 | Drogue Projected Area (ft²): | 12.5664 | Main Projected Area (ft²): | 113.0972 | Drogue Shock Load with Reduction Factor (lbf): | 246.7601
Stage Dry Weight (lbs): | 160 | Drogue Drag Coeff: | 2.2 | Main Drag Coeff: | 2.2 | Main Shock Load at Inf. Mass (lbf): | 2160 | 4320 | 5400 | 6480
Air Density at Apogee (slug/ft^3): | 0.0015992 | Drogue Shock Loading Coeff: | 1.5 | Main Shock Loading Coeff: | 1.5 | Main Shock Load with Reduction Factor (lbf): | 1080 |  | lbf | Newtons
Air Density at Main Deployment (slug/ft^3): | 0.0021152 | Drogue Shock Reduction Factor: | 0.5 | Main Shock Reduction Factor: | 0.5 | Kinetic Energy on Impact (ft-lbf): | 1467.2271 | Drogue | 493.5203 | 2195.2875
Air Density at Ground (slug/ft^3): | 0.0021795 | Max Terminal Velocity Under Drogue (ft/s): | 85.0772 | Main Terminal Velocity (ft/s): | 24.6583 | Drift Distance (ft): | 3553.924 | Main | 2160 | 9608.1587
Wind Speed (ft/s): | 22 | Descent Time (s): | 161.542
Option 8 Main: 144" PDA Drogue: 36" PDA | [6 empty] | FOS: | 2 | 2.5 | 3
Ground Altitude AMSL (ft): | 2934 | Ground Velocity at Drogue Deployment (ft/s): | 100 | Air Velocity at Main Deployment (ft/s): | 98.6334 | Landing Air Velocity (ft/s): | 24.2916 | Minimum | Acceptable | Goal
Apogee AGL(ft): | 10000 | Drogue Projected Diameter (in): | 36 | Main Projected Diameter (in): | 144 | Drogue Shock Load at Inf. Mass (lbf): | 277.6051 | 555.2103 | 694.0129 | 832.8154
Main Deployment Altitude AGL (ft): | 1000 | Drogue Projected Area (ft²): | 7.0686 | Main Projected Area (ft²): | 113.0972 | Drogue Shock Load with Reduction Factor (lbf): | 138.8026
Stage Dry Weight (lbs): | 160 | Drogue Drag Coeff: | 2.2 | Main Drag Coeff: | 2.2 | Main Shock Load at Inf. Mass (lbf): | 3840 | 7680 | 9600 | 11520
Air Density at Apogee (slug/ft^3): | 0.0015992 | Drogue Shock Loading Coeff: | 1.5 | Main Shock Loading Coeff: | 1.5 | Main Shock Load with Reduction Factor (lbf): | 1920 |  | lbf | Newtons
Air Density at Main Deployment (slug/ft^3): | 0.0021152 | Drogue Shock Reduction Factor: | 0.5 | Main Shock Reduction Factor: | 0.5 | Kinetic Energy on Impact (ft-lbf): | 1467.2271 | Drogue | 277.6051 | 1234.8492
Air Density at Ground (slug/ft^3): | 0.0021795 | Max Terminal Velocity Under Drogue (ft/s): | 113.4362 | Main Terminal Velocity (ft/s): | 24.6583 | Drift Distance (ft): | 2900.168 | Main | 3840 | 17081.171
Wind Speed (ft/s): | 22 | Descent Time (s): | 131.8258
Option 9 Main: 120" PDA Drogue: 72" PDA | [6 empty] | FOS: | 2 | 2.5 | 3
Ground Altitude AMSL (ft): | 2934 | Ground Velocity at Drogue Deployment (ft/s): | 100 | Air Velocity at Main Deployment (ft/s): | 49.3167 | Landing Air Velocity (ft/s): | 29.1499 | Minimum | Acceptable | Goal
Apogee AGL(ft): | 10000 | Drogue Projected Diameter (in): | 72 | Main Projected Diameter (in): | 120 | Drogue Shock Load at Inf. Mass (lbf): | 1110.4206 | 2220.8412 | 2776.0515 | 3331.2618
Main Deployment Altitude AGL (ft): | 1000 | Drogue Projected Area (ft²): | 28.2743 | Main Projected Area (ft²): | 78.5397 | Drogue Shock Load with Reduction Factor (lbf): | 555.2103
Stage Dry Weight (lbs): | 160 | Drogue Drag Coeff: | 2.2 | Main Drag Coeff: | 2.2 | Main Shock Load at Inf. Mass (lbf): | 666.6667 | 1333.3333 | 1666.6667 | 2000
Air Density at Apogee (slug/ft^3): | 0.0015992 | Drogue Shock Loading Coeff: | 1.5 | Main Shock Loading Coeff: | 1.5 | Main Shock Load with Reduction Factor (lbf): | 333.3333 |  | lbf | Newtons
Air Density at Main Deployment (slug/ft^3): | 0.0021152 | Drogue Shock Reduction Factor: | 0.5 | Main Shock Reduction Factor: | 0.5 | Kinetic Energy on Impact (ft-lbf): | 2112.8071 |  | 1110.4206 | 4939.3969
Air Density at Ground (slug/ft^3): | 0.0021795 | Max Terminal Velocity Under Drogue (ft/s): | 56.7181 | Main Terminal Velocity (ft/s): | 29.59 | Drift Distance (ft): | 4704.9528 |  | 666.6667 | 2965.4811
Wind Speed (ft/s): | 22 | Descent Time (s): | 213.8615
Option 10 Main: 120" PDA Drogue: 60" PDA | [6 empty] | FOS: | 2 | 2.5 | 3
Ground Altitude AMSL (ft): | 2934 | Ground Velocity at Drogue Deployment (ft/s): | 100 | Air Velocity at Main Deployment (ft/s): | 59.18 | Landing Air Velocity (ft/s): | 29.1499 | Minimum | Acceptable | Goal
Apogee AGL(ft): | 10000 | Drogue Projected Diameter (in): | 60 | Main Projected Diameter (in): | 120 | Drogue Shock Load at Inf. Mass (lbf): | 771.1254 | 1542.2508 | 1927.8135 | 2313.3762
Main Deployment Altitude AGL (ft): | 1000 | Drogue Projected Area (ft²): | 19.6349 | Main Projected Area (ft²): | 78.5397 | Drogue Shock Load with Reduction Factor (lbf): | 385.5627
Stage Dry Weight (lbs): | 160 | Drogue Drag Coeff: | 2.2 | Main Drag Coeff: | 2.2 | Main Shock Load at Inf. Mass (lbf): | 960 | 1920 | 2400 | 2880
Air Density at Apogee (slug/ft^3): | 0.0015992 | Drogue Shock Loading Coeff: | 1.5 | Main Shock Loading Coeff: | 1.5 | Main Shock Load with Reduction Factor (lbf): | 480 |  | lbf | Newtons
Air Density at Main Deployment (slug/ft^3): | 0.0021152 | Drogue Shock Reduction Factor: | 0.5 | Main Shock Reduction Factor: | 0.5 | Kinetic Energy on Impact (ft-lbf): | 2112.8071 | Drogue | 771.1254 | 3430.1367
Air Density at Ground (slug/ft^3): | 0.0021795 | Max Terminal Velocity Under Drogue (ft/s): | 68.0617 | Main Terminal Velocity (ft/s): | 29.59 | Drift Distance (ft): | 4051.1968 | Main | 960 | 4270.2928
Wind Speed (ft/s): | 22 | Descent Time (s): | 184.1453
Option 11 Main: 120" PDA Drogue: 48" PDA | [6 empty] | FOS: | 2 | 2.5 | 3
Ground Altitude AMSL (ft): | 2934 | Ground Velocity at Drogue Deployment (ft/s): | 100 | Air Velocity at Main Deployment (ft/s): | 73.975 | Landing Air Velocity (ft/s): | 29.1499 | Minimum | Acceptable | Goal
Apogee AGL(ft): | 10000 | Drogue Projected Diameter (in): | 48 | Main Projected Diameter (in): | 120 | Drogue Shock Load at Inf. Mass (lbf): | 493.5203 | 987.0405 | 1233.8007 | 1480.5608
Main Deployment Altitude AGL (ft): | 1000 | Drogue Projected Area (ft²): | 12.5664 | Main Projected Area (ft²): | 78.5397 | Drogue Shock Load with Reduction Factor (lbf): | 246.7601
Stage Dry Weight (lbs): | 160 | Drogue Drag Coeff: | 2.2 | Main Drag Coeff: | 2.2 | Main Shock Load at Inf. Mass (lbf): | 1500 | 3000 | 3750 | 4500
Air Density at Apogee (slug/ft^3): | 0.0015992 | Drogue Shock Loading Coeff: | 1.5 | Main Shock Loading Coeff: | 1.5 | Main Shock Load with Reduction Factor (lbf): | 750 |  | lbf | Newtons
Air Density at Main Deployment (slug/ft^3): | 0.0021152 | Drogue Shock Reduction Factor: | 0.5 | Main Shock Reduction Factor: | 0.5 | Kinetic Energy on Impact (ft-lbf): | 2112.8071 | Drogue | 493.5203 | 2195.2875
Air Density at Ground (slug/ft^3): | 0.0021795 | Max Terminal Velocity Under Drogue (ft/s): | 85.0772 | Main Terminal Velocity (ft/s): | 29.59 | Drift Distance (ft): | 3397.4407 | Main | 1500 | 6672.3324
Wind Speed (ft/s): | 22 | Descent Time (s): | 154.4291
Option 12 Main: 120" PDA Drogue: 36" PDA | [6 empty] | FOS: | 2 | 2.5 | 3
Ground Altitude AMSL (ft): | 2934 | Ground Velocity at Drogue Deployment (ft/s): | 100 | Air Velocity at Main Deployment (ft/s): | 98.6334 | Landing Air Velocity (ft/s): | 29.1499 | Minimum | Acceptable | Goal
Apogee AGL(ft): | 10000 | Drogue Projected Diameter (in): | 36 | Main Projected Diameter (in): | 120 | Drogue Shock Load at Inf. Mass (lbf): | 277.6051 | 555.2103 | 694.0129 | 832.8154
Main Deployment Altitude AGL (ft): | 1000 | Drogue Projected Area (ft²): | 7.0686 | Main Projected Area (ft²): | 78.5397 | Drogue Shock Load with Reduction Factor (lbf): | 138.8026
Stage Dry Weight (lbs): | 160 | Drogue Drag Coeff: | 2.2 | Main Drag Coeff: | 2.2 | Main Shock Load at Inf. Mass (lbf): | 2666.6667 | 5333.3333 | 6666.6667 | 8000
Air Density at Apogee (slug/ft^3): | 0.0015992 | Drogue Shock Loading Coeff: | 1.5 | Main Shock Loading Coeff: | 1.5 | Main Shock Load with Reduction Factor (lbf): | 1333.3333 |  | lbf | Newtons
Air Density at Main Deployment (slug/ft^3): | 0.0021152 | Drogue Shock Reduction Factor: | 0.5 | Main Shock Reduction Factor: | 0.5 | Kinetic Energy on Impact (ft-lbf): | 2112.8071 | Drogue | 277.6051 | 1234.8492
Air Density at Ground (slug/ft^3): | 0.0021795 | Max Terminal Velocity Under Drogue (ft/s): | 113.4362 | Main Terminal Velocity (ft/s): | 29.59 | Drift Distance (ft): | 2743.6847 | Main | 2666.6667 | 11861.9243
Wind Speed (ft/s): | 22 | Descent Time (s): | 124.7129